## Sheet1
Consultation Register - WBP PPC
Denotes no Response to Date
Party | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number | Date | Sent or Received | Nature | Reference Number
SGA | 2023-08-29 | Sent | Initial Consultation, Meeting Request | 1 | 2023-09-08 | Received | Confirming Desire to meet to engage | 2 | 2023-09-20 | Sent | Draft Drawings | 3 | 2023-10-27 | Sent | Provide draft ITA and other items | 4 | 2023-11-02 | Received | Confirmation of review. Feedback is to be distrubuted by AT. | 5
AT | 2023-08-29 | Sent | Initial Consultation, Meeting Request | 1 | 2023-08-29 | Received | Confirming Katherin Dorofaeff and Rory Power will facilitate Meetings | 2 | 2023-10-05 | Sent | Drawings and Brief before meeting | 3 | 2023-10-09 | Sent | Post Meeting Notes | 4 | 2023-10-10 | Sent | Draft Road X Sections | 5 | 2023-10-24 | Received | Feedback on modelling assumptions. | 6 | 2023-10-27 | Sent | Provide Draft ITA | 7 | 2023-10-31 | Received | AT Technical Feedback | 8 | 2023-11-01 | Sent | Confirmation of Receipt of Technical Feedback | 9 | 2023-11-21 | Sent | Response table to AT memo dated 30 Oct, and associated drawings | 10 | 2023-12-13 | Received | Response to NCL Table | 11
Upper Harbour Local Board | 2023-08-29 | Sent | Initial Consultation | 1
Herald Island Environmental Group | 2023-08-29 | Sent | Initial Consultation | 1 | 2024-08-02 | Sent | Follow up and provide initial consultation emails | 2 | 2024-08-05 | Received | Request for update on PPC status | 3 | 2024-08-12 | Sent | Update on Status of WBP/WG | 4 | 2024-08-15 | Received | Agree to meeting at some point | 5 | 2024-08-16 | Received | Specific meeting limes | 6 | 2024-08-19 | Sent | Agree to meet 2pm 26/8/24 | 7 | 2024-10-17 | Sent | Update that PPC will be notified, outline provisions that protect the environment | 8 | 2024-10-17 | Received | Response from Annette Mitchell | 9
Royal Forest and Bird Society | 2023-08-29 | Sent | Initial Consultation | 1
Healthy Waters | 2023-08-29 | Sent | Initial Consultation, Meeting Request | 1 | 2023-09-12 | Received | No catchment manager for area - will be in touch once in place | 2 | 2023-09-13 | Received | Todd Elder - encouraging Healthy Waters to Resource with PPC | 3 | 2023-11-07 | Received | Confirmation of HW contacts, and meeting request | 4 | 2023-11-08 | Sent | Confirmation of meeting set for Friday 10th November | 5 | 2023-11-09 | Received | Confirmation can attend. Query about who Phil Jaggard is. | 6 | 2024-11-09 | Sent | Clarification of who Phil Jaggard is | 7 | 2023-11-09 | Sent | Provide draft SMP and Infrastructure reports | 8 | 2023-11-10 | Sent | Provide draft flood report | 9 | 2023-11-13 | Received | Request for appendices, Hydraulic Modelling and precint provisions | 10 | 2023-11-21 | Sent | Follow up on feedback request | 11 | 2023-11-21 | Received | Confirmation feedback in process - due end of week. Request document appendix | 12 | 2023-11-22 | Sent | Infrastructure report with appendicies provided | 13 | 2023-11-22 | Received | SMP and Flood Report Appendeces Request | 14 | 2023-11-24 | Sent | Provide SMP and Flood with all appendices | 15
Watercare | 2023-08-29 | Sent | Initial Consultation, Meeting Request | 1 | 2023-09-28 | Sent | Engineers Summary of Changes | 2 | 2023-10-05 | Received | Introduction of Lars and Amber. Agree to Meeting | 3 | 2023-10-06 | Sent | Meeting arranged for Monday 9 October, 4pm | 4 | 2023-10-16 | Sent | Notes from meeting | 5 | 2023-10-19 | Received | Response from Amber. Complete form for a developer consultation | 6 | 2023-10-27 | Sent | Return Development Consultation Form. Will provide Infrastructure report next week | 7 | 2023-11-15 | Sent | Provided draft infrastructure report | 8 | 2023-11-23 | Received | Confirmation of feedback due 5th December | 9
NZDF | 2023-08-29 | Sent | Initial Consultation | 1 | 2023-08-30 | Received | Request to send communication to Rebecca Davies and Rob Owen, Exclude Kevin Short | 2 | 2023-10-04 | Sent | Key Topics and Meeting Request | 3 | 2023-10-16 | Sent | Follow up on meeting request | 4 | 2023-10-19 | Sent | Notes from meeting | 5
Auckland Council Plans and Places
Auckland Council Parks and Open Space | 2023-09-06 | Sent | Initial Consultation, Meeting Request | 1 | 2023-09-07 | Received | All comms to Hester Gerber. Discuss interface with Council Open Spaces on BCR and Trig | 2 | 2023-09-20 | Sent | Description of Boundary treatment, possible link | 3 | 2023-10-12 | Sent | Summary of Meeting | 4 | 2023-10-25 | Sent | Revised Precint Plan | 5
Te Kawerau a Maki | 2023-08-29 | Sent | Initial Consultation, ask if further CIA needed | 1 | 2023-10-19 | Sent | Follow up for response | 2 | 2023-11-09 | Sent | CIA Summary of Likely Issues. Provide SMP and Archaeological Report | 3 | 2024-09-09 | Sent | Update on PPC and Provide SMP | 4 | 2024-09-12 | Received | Ashleigh McDonald acknowledge receipt and ask for timeframes | 5 | 2024-09-26 | Sent | Repond with Council Clause 25 estimated timelines | 6
Ngāti Manuhiri | 2023-08-29 | Sent | Ask if interest in land | 1 | 2023-09-05 | Received | Defer to Te Kawerau a Maki to lead in this area | 2
Ngāti Maru | 2023-08-29 | Sent | Ask if interest in land | 1 | 2023-10-05 | Received | Note to please remove office@ngatimaru.iwi.nz from consultation chain. Only consult eu@ngatimaru.iwi.nz | 2 | 2023-11-17 | Sent | Consultation Follow up
Ngāti Paoa Iwi Trust and Trust Board | 2023-08-29 | Sent | Ask if interest in land | 1 | 2023-11-17 | Sent | Consultation Follow up | 2
Ngāti Te Ata | 2023-08-29 | Sent | Ask if interest in land | 1 | 2023-08-30 | Received | Confirmation no engagement needed | 2
Ngāti Whātua o Kaipara | 2023-08-29 | Sent | Ask if interest in land | 1 | 2023-11-17 | Sent | Consultation Follow up | 2
Ngāti Whātua Ōrākei Trust Board | 2023-08-29 | Sent | Ask if interest in land | 1 | 2023-11-17 | Sent | Consultation Follow up | 2
Te Rūnanga o Ngāti Whātua | 2023-08-29 | Sent | Ask if interest in land | 1 | 2023-09-08 | Received | Phone call from Glenn Wilcox. Noting interest and will complete a CIA | - | 2023-09-08 | Sent | Email Confirming Phone Conversation and that land parcels are part of the Waipareira Block | 3 | 2023-09-18 | Sent | Follow up on if a CIA is required | 4 | 2023-11-17 | Sent | Consultation Follow up | 5
Te Ākitai Waiohua | 2023-08-29 | Sent | Ask if interest in land | 1 | 2023-11-17 | Sent | Consultation Follow up | 2
Private Landowners
145 Brigham Creek Road | 2023-08-29 | Received | Signed approval form (met in person) | 1 | 2023-11-30 | Sent | Provided Draft Application Package | 2 | 2024-10-07 | Sent | Update on PPC | 3 | 2024-10-07 | Received | Confirmed update received
153 Brigham Creek Road | 2023-08-28 | Sent | Seek Landowner approval | 1 | 2023-08-30 | Received | Spark Request for Meeting in October | 2 | 2023-08-30 | Sent | Agree to meeting - but request for site access ASAP | 3 | 2023-11-21 | Sent | Provided: SMP, Flooding, Ecology | 4 | 2023-11-30 | Sent | Provided Draft Application Package | 5 | 2023-12-20 | Received | Query about file access and zoning | 6
159 Brigham Creek Road | 2023-08-28 | Sent | Seek Landowner approval | 1 | 2023-09-14 | Received | Signed Approval Letter | 2 | 2023-11-30 | Sent | Provided Draft Application Package | 3 | 2024-05-01 | Sent | Provided update on SMP/Flooding | 4 | 2024-10-07 | Sent | Update on PPC | 5
96A Trig Road | 2023-08-28 | Sent | Seek Landowner approval | 1 | 2023-09-29 | Received | Signed Approval Letters | 2 | 2023-10-24 | Received | Solicitor email confirming purchase | 3 | 2024-10-07 | Sent | Update on PPC | 4
96 Trig Road | 2023-08-28 | Sent | Seek Landowner approval | 1 | 2023-09-06 | Received | Signed owner Approval, subject to providing additional PPC info as produced | 2 | 2023-11-30 | Sent | Provided Draft Application Package | 3 | 2024-10-07 | Sent | Update on PPC | 4
Neighbours
61 Trig Road | 2023-09-12 | Sent | Generic Neighbour Letter | 1
63 Trig Roadg | 2023-09-12 | Sent | Generic Neighbour Letter | 1
65 Trig Road | 2023-09-12 | Sent | Generic Neighbour Letter | 1
67 Trig Road | 2023-09-12 | Sent | Generic Neighbour Letter | 1
163 Brigham Creek Road | 2023-09-12 | Sent | Generic Neighbour Letter | 1 | 2024-07-10 | Sent | Follow up email with PPC update
6 Spedding Road | 2023-09-12 | Sent | Generic Neighbour Letter | 1
28 Mamari Road | 2023-09-12 | Sent | Generic Neighbour Letter | 1 | 2023-10-02 | Received | Request for land to be included in PPC Area | 2 | 2023-10-04 | Sent | Basis for refusal to include land in PPC Area | 3 | 2023-10-09 | Received | Request assistance with secondary PPC on client's land, and planner's details | 4 | 2023-10-10 | Sent | Deny secondary PPC request, provide Campbell Brown Details | 5
28A Mamari Road | 2023-09-12 | Sent | Generic Neighbour Letter | 1