## Funding Plan
Draft Funding Plan template to support a structure plan
Project details |  |  |  |  | Project timing |  |  | Project delivery by Council Group |  |  | Project delivery by Crown |  |  | Project delivery by Developer |  |  | Risk assessment |  |  |  | Summary
Infrastructure type | Infrastructure sub-type | Final asset owner | Party responsible for OPEX, maintenance, depreciation | Project name | When is the project required (demand date) | What is the project demand date based on | What is the project completion date (if different to demand date) | Is Council Group (AT, Watercare or Council) assumed to deliver any portion of this project | Has Council Group indicated commitment to this? If yes, in what document | When has Council Group planned to deliver this project/part of this project | Is Crown assumed to deliver any part of this project | Has Crown indicated commitment to this? If yes, in what document | When does Crown plan to deliver this project/part of this project | Are you (developer/applicant) delivering the project directly (either in part or in full) | Are you (developer/applicant) proposing the IFF Act is used to deliver the project (either in part or in full) | Is another developer or third party delivering the project (either in part or in full) | What evidence is available that this project will be delivered (by the parties identified at the timeframe identified) | To understand the level of risk that the development will occur without the infrastructure, does this project relate to an development trigger in your Precinct Provisions/Plan? If yes, reference the trigger | Level of risk that the project will be delivered (by the parties identified at the timeframe identified) | Risk or impact on the development if the project is not delivered at the timeframe identified
e.g. transport | e.g. arterial road | e.g. AT | e.g. AT | xyz | e.g. 2027 | e.g. based on council's growth model AGSv1.1 | e.g. 2030 | e.g. yes 100% of the project, yes 50% of the project, no as all developer delivered | e.g. yes, project included in 30y DC Policy | e.g. 2030 | e.g. yes 100% of the project, yes 50% of the project, no as all developer delivered | e.g. yes, in NLTP | e.g. 2030 | e.g. 100% of the project to be developer provided by the applicant | e.g. yes / no | e.g. this project is assumed to be delivered by a separate developer as part of their approved plan change in 2023 | e.g. the project is in the RLTP. The applicant has drafted an Infrastructure Funding Agreement for the delivery of this project | e.g. does this plan change include an infrastructure trigger relating to this project? E.g. 'no' as considered standard developer mitigation required under the RMA before any development commences | e.g. low risk, medium risk, high risk, with explanation of why this risk profile is applicable | e.g. if the project is delayed by 2 years, this means xyz | e.g. this road is required to serve the development and is proposed to be constructed prior to occupation of dwellings by year 2030 by xyz
Transport | Local active-mode connection | AT | AT | AMC from FPH Plan Change area to Ngākōroa station | 2030 | Based on the opening of FPH 1st building to habituate public transport use to site. | 2030 | FPH are currently in discussions with AT and KiwiRail and it will be funded by a combination of parties or one. | no | N/A | no | N/A | N/A | FPH are currently in discussions with AT and KiwiRail and it will be funded by a combination of parties or one. | no | no | Minutes of meetings exist capturing discussions between AT, KiwiRail and FPH on intentions to deliver this project. | No as considered standard developer mitigation required under the RMA before any development commences [I.e. it is expected to be addressed at consenting stage through conditions of consent] | Medium risk, discussions have been held with AT and KiwiRail on the requirement for the pathway along the rail corridor. Discussions with the owner of the land parcel between FPH and the Station are yet to be held. | If the project is delayed employees would have to find alternative access to site | This AMC is beneficial to the development and is proposed to be constructed prior to occupation by year 2030 by FPH and AT.
Transport | Rail Infrastructure | KiwiRail | KiwiRail | Ngākōroa Train Station | 2030 | Based on the opening of the 1st building to habituate public transport use to site. Also based wider demand for the station in Drury West. | 2026 | No | N/A | N/A | Yes 100% of the project | Yes, in the Supporting Growth Programme, funded as within the New Zelanad Upgrade Programme. | 2026 | No | No | No | The project is currently under construction and expected to be completed by 2026 | No | Low risk. Construction is underway and ongoing | Increased congestion on roads to due a large proportion of employees unable to take public transport to work and instead need to drive. | The Station is beneficial to the development and is under construction by KiwiRail and expected to be completed by 2026
Water | Local Network | Veolia | Veolia | Connection to Flanagan Road BSP with additional connection to the north. | 2050+ | Not intially required for the FPH Plan Change area; timing would depend on actual demand on-site | 2050+ | No | N/A | N/A | No | N/A | N/A | No | No | yes, shared funding between other developers expected | N/A | no as considered standard developer mitigation required under the RMA before any development commences | Low risk. Network expansion will be required to serve surrounding developments. | Given on-site servcing is an option for this site, restriction on development would be limited if this project is delayed. | The expansion of the network from FPH to Flanagan Road BSP with additional connection to the north is required for wider servicing but may not be required for the FPH site for some time (likely not required until closer to 2050, due to onsite servicing being available for the first three buildings).
Wastewater | Local Network | Veolia | Veolia | Wastewater rising main from FPH PC to manhole 13. | 2047 | FPH Plan Change - when FPH's onsite wastewater treatment capacity is reached. | 2047 | No | N/A | N/A | No | N/A | N/A | No | No | yes, shared funding between developers expected. | N/A | no as considered standard developer mitigation required under the RMA before any development commences | Low risk. Network expansion will be required to serve surrounding developments. | If the project is delayed, and if water demand on site could not be accommodated with on-site resources then development would be restricted , until the upgrade is constructed and operational | The installation of a rising main from FPH to Manhole 13 is required to connect to the bulk Watercare wastewater network. This is not required until around 2047 as the site will be serviced onsite for initial stages.
Transport | Arterial Road | NZTA | NZTA | Interim upgraded intersection at the intersection of Karaka Road / Oira Road / proposed site driveway (roundabout with two approach lanes in each direction or equivalent interim traffic signals, including active mode facilities). | 2030 | Prior to the occupation of the first building for safe employee access to and from FPH Plan Change area. | N/A | No | N/A | N/A | No | N/A | N/A | Yes, percentage contribution dependent on other developers (of the Waipupuke Precinct) | No | The funding for this upgrade will be found as required but it could be cost shared. | N/A | Yes, this proposed plan change includes a development trigger in the precinct previsions in Table IX 6.2 | Low risk, given both the FPH plan change and the Waipupuke approved plan includes the requirement for this upgrade to be completed. | If the project is delayed, site occupation will be delayed. | This intersection upgrade is required to serve as the first safe access to the development by vehicles on Karaka Road and is proposed to be completed prior to the completion of the Waipupuke or FPH development (Building 1) by these developers by the year 2030.
Transport | Arterial Road | NZTA | NZTA | Ultimate upgraded intersection at the intersection of Karaka Road and Oira Road (roundabout with three approach lanes from FPH or equivalent interim traffic signals, including active mode facilities). | 2042-2047 | Sensitivity testing of traffic modelling of the intersections | N/A | No | N/A | N/A | N/A | N/A | N/A | 100% of the project to be developer provided by the applicant | No | No | N/A | Yes, this proposed plan change includes a development trigger in the precinct previsions in Table IX 6.2 | Medium risk of delivery at the indicated timeframe as building development (GFA) is dependent on FPH growth | If the project is delayed, development would be restricted as per the precinct provision, until the upgrade is constructed and operational | This intersection upgrade is required to ease traffic congestion from the development and is proposed to be completed between 2042 - 2047.
Transport | Arterial Road | NZTA | NZTA | Second site access, including active mode facilities, located generally near the eastern boundary of the site | 2047 | Sensitivity testing of traffic modelling of the intersections | N/A | Unknown | N/A | N/A | Unknown | N/A | N/A | Yes, percentage contribution dependent on contributions from AT and or NZTA | No | No | N/A | Yes, this proposed plan change includes a development trigger in the precinct previsions in Table IX 6.2 | Medium risk of delivery at the indicated timeframe as building development (GFA) is dependent on FPH growth | If the project is delayed, development would be restricted as per the precinct provision, until the upgrade is constructed and operational | This intersection upgrade is required to ease traffic congestion from the development and is proposed to be completed by 2047. Possibility of joint approach with AT to tie in future bus route to train station from SH22 and FPH second entrance
Wastewater | Trunk Network | Watercare | Watercare | Hingaia WW PS Upgrade | 2031-2035 | Based on Counci's FDS anticipating significant growth in the region | Planned delivery in this timeframe | Yes, 100% of the project | Yes, Watercare Asset Management Plan 2021-2041 | 2021-2031 | No | N/A | N/A | No | No | No | The project is identified in Watercares Asset Management Plan (2021-2041) as part of the Southern Interceptor augmentation Programme, for delivery 2021-2031. | No as considered standard developer mitigation required under the RMA before any development commences (required under Chapter E38 - Subdivision of the AUP(OP)). | Low risk, given the area is anticipated for high growth in the Auckalnd Councils FDS and bulk wastewater infrastructure is required to service the area. | No impact if this project is delayed as it not required for FPH development until closer to 2050. | This project is required to increase trunk capacity in the surrounding area to support anticipated future growth and is proposed to be completed between 2031-2035.
Wastewater | Trunk Network | Watercare | Watercare | Bremner Road PS Upgrade | 2031-2035 | Based on Counci's FDS anticipating significant growth in the region | Planned delivery in this timeframe | Yes, 100% of the project | Yes, Watercare Asset Management Plan 2021-2041 | 2021-2031 | No | N/A | N/A | No | No | No | The project is identified in Watercares Asset Management Plan (2021-2041) as part of the Southern Interceptor augmentation Programme, for delivery 2021-2031. | No as considered standard developer mitigation required under the RMA before any development commences (required under Chapter E38 - Subdivision of the AUP(OP)). | Low risk, given the area is anticipated for high growth in the Auckalnd Councils FDS and bulk wastewater infrastructure is required to service the area. | No impact if this project is delayed as it not required for FPH development until closer to 2050. | This project is required to increase trunk capacity in the surrounding area to support anticipated future growth and is proposed to be completed between 2031-2035.
Wastewater | Trunk Network | Watercare | Watercare | Drury West Trunk (through to Bremner Road MH13) | 2031-2035 | Based on Counci's FDS anticipating significant growth in the region | Planned delivery in this timeframe | Yes, 100% of the project | Yes, Watercare Asset Management Plan 2021-2041 | 2031-2035 | No | N/A | N/A | No | No | No | The project is identified in Watercares Asset Management Plan (2021-2041) as part of the Southern Interceptor augmentation Programme, for delivery 2021-2031. | No as considered standard developer mitigation required under the RMA before any development commences (required under Chapter E38 - Subdivision of the AUP(OP)). | Low risk, given the area is anticipated for high growth in the Auckalnd Councils FDS and bulk wastewater infrastructure is required to service the area. | No impact if this project is delayed as it not required for FPH development until closer to 2050. | This project is required to increase trunk capacity in the surrounding area to support anticipated future growth and is proposed to be completed between 2031-2035.

## Development timing assumptions
For the purpose of this funding plan, the following development timing assumptions have been made:
The opening year of the first building (when Building 1 will be occupied) will be approximately 2030 or just after
The assumption for when the gfa will exceed 79,750m2 (when the Ultimate Oira Road intersection will be required) will be between 2042 and 2047.
The assumption of when the gfa will exceed 88,000m2 (when a second site access is required) will be from 2047+.

## Infrastructure included
Infrastructure to be included in a Funding Plan
This template should include all infrastructure projects relevent to the Structue Plan area e.g. projects within the area and projects located outside the area which are required to service the area and are being relied upon.
This includes developer mitigation projects and bulk projects to be provded by Council Group or a Crown entity
Infrastructure Type | Infrastructure subcategory
Transport | Arterial roads
Key collector roads
Collector roads
Local roads
Strategic projects by NZTA (if relevant)
KiwiRail projects (if relevant)
Water | Bulk network
Local network
Wastewater | Bulk network
Local network
Stormwater | Catchment scale projects
Piped network
Open Space | Sports parks
Suburb parks
Neighbourhood parks
Civic spaces
Local parks
Esplanade reserves
Greenways
Community Facilities | All council group community infrastructure (library, leisure and aquatic facilities)